## Slide 2: Where We Are Now

## Slide 3: Rationale for Reducing Project Duration
Time Is Money: Cost-Time Tradeoffs
  Reducing the time of a critical activity usually incurs additional direct costs.
    Cost-time solutions focus on reducing (crashing) activities on the critical path to shorten overall duration of the project.
  Reasons for imposed project duration dates:
    Time-to-market pressures
    Unforeseen delays
    Incentive contracts (bonuses for early completion)
    Imposed deadlines and contract commitments
    Overhead and public goodwill costs
    Pressure to move resources to other projects

## Slide 4: Options for Accelerating Project Completion
Resources Not Constrained
  Adding resources
  Outsourcing project work
  Scheduling overtime
  Establishing a core project team
  Do it twice—fast and then correctly
Resources Constrained
  Fast-tracking
  Critical-chain
  Reducing project scope
  Compromise quality

## Slide 5: Explanation of Project Costs
Project Indirect Costs
  Costs that cannot be associated with any particular work package or project activity.
    Supervision, administration, consultants, and interest
  Costs that vary (increase) with time.
    Reducing project time directly reduces indirect costs.
Project Direct Costs
  Normal costs that can be assigned directly to a specific work package or project activity.
    Labor, materials, equipment, and subcontractors
  Crashing activities increases direct costs.

## Slide 6: Reducing Project Duration to Reduce Project Cost
Compute total costs for specific durations and compare to benefits of reducing project time.
Search critical activities for lowest direct-cost activities to shorten project duration.
Identifying direct costs to reduce project time
Gather information about direct and indirect costs of specific project durations.

## Slide 7: Project Cost–Duration Graph
FIGURE 9.1

## Slide 8: Constructing a Project Cost–Duration Graph
Find total direct costs for selected project durations.
Find total indirect costs for selected project durations.
Sum direct and indirect costs for these selected project durations.
Compare additional cost alternatives for benefits.

## Slide 9: Constructing a Project Cost–Duration Graph
Determining Activities to Shorten
  Shorten the activities with the smallest increase in cost per unit of time.
  Assumptions:
    The cost relationship is linear.
    Normal time assumes low-cost, efficient methods to complete the activity.
    Crash time represents a limit—the greatest time reduction possible under realistic conditions.
    Slope represents a constant cost per unit of time.
    All accelerations must occur within the normal and crash times.

## Slide 10: Activity Graph
FIGURE 9.2

## Slide 11: Cost–Duration Trade-off Example
FIGURE 9.3

## Slide 12: Cost–Duration Trade-off Example (cont’d)
FIGURE 9.3 (cont’d)

## Slide 13: Cost–Duration Trade-off Example (cont’d)
FIGURE 9.4

## Slide 14: Cost–Duration Trade-off Example (cont’d)
FIGURE 9.4 (cont’d)

## Slide 15: Summary Costs by Duration
FIGURE 9.5

## Slide 16: Project Cost–Duration Graph
FIGURE 9.6

## Slide 17: Practical Considerations
Using the Project Cost–Duration Graph
Crash Times
Linearity Assumption
Choice of Activities to Crash Revisited
Time Reduction Decisions and Sensitivity

## Slide 18: What if Cost, Not Time Is the Issue?
Commonly Used Options for Cutting Costs
  Reducing project scope
  Having owner take on more responsibility
  Outsourcing project activities or even the entire project
  Brainstorming cost savings options

## Slide 19: Key Terms
Crashing
Crash point
Crash time
Direct costs
Fast-tracking
Indirect costs
Outsourcing
Project cost–duration graph

## Slide 20: Project Priority Matrix: Whitbread Project
FIGURE C9.1